## Sheet1
URS ID | USER REQ DESCRIPTION | TECH SPEC ID | TEST SCRIPT ID | INCIDENT REPORT ID | TESTING STATUS | ASSOCIATED DOCUMENTATION
FR-01 | The microservice shall be capable of converting files between a defined set of inputs and outputs. | TS-01 - TS-05 | TEST-01 | IR-01 - IR-03 | Testing Complete | Training Guide [Rev: 1-May-2020]
Support Policy [Rev: 1-May-2020]
FR-02 | The microservice shall be capable of presenting the file to the user after the conversion process. | TS-01 - TS-05 | TEST-01 | IR-01 - IR-03 | Testing Complete | Training Guide [Rev: 1-May-2020]
Support Policy [Rev: 1-May-2020]
FR-03 | The microservice team shall create a handoff plan explaining how to integrate the microservice to the CMS. | N/A | Test-02 | N/A | Testing Complete | Final Report Section 7.1 [Rev: 30-Apr-2020]
FR-04.1 | The project team shall identify and create use-cases for potential users of the microservice within the CMS. | N/A | Test-02 | N/A | Testing Complete | Final Report Section 4.2 [Rev: 28-Apr-2020]
FR-05 | The project team shall create a graphic user interface for the user to utilize the microservice within the CMS. | N/A | N/A | N/A | Out-of-Scope | N/A
NFR-01 | The microservice shall be ready for implementation by the end of April 2020. | N/A | Test-03 | N/A | Testing Complete | Gantt Chart [Rev: 17-Apr-2020]
NFR-02 | The project team shall fully integrate the microservice into HAX CMS. | N/A | N/A | N/A | Out-of-Scope | N/A
NFR-03 | The microservice shall include a disclaimer warranting use to non-copyrighted material or copyrighted material with granted permission. | N/A | Test-03 | N/A | Testing Complete | GitHub ReadME (https://github.com/elmsln/Pandoc-Service) [Rev: 14-Apr-2020]
NFR-04 | The microservice shall be free of any bugs and/or errors by release time. | TS-05 | TEST-01 | IR-01 - IR-03 | Testing Complete | N/A
NRF-05 | File conversions shall be successful a minimum of 97% of the time. | TS-05 | TEST-01 | IR-01 - IR-03 | Testing Complete | N/A
Note: Requirements with a strike-through notation are now out-of-scope for this project launch.