## Sheet1
IST 440 - HAX CMS MICROSERVICE GANTT CHART
TASK ID | TASK DESCRIPTION | PREDECESSOR TASK | DURATION (Hours) | TASK OWNER | time axis 2020-02-03 to 2020-05-04
1 | PLAN |  |  |  | 2020-03-07: Spring Break
1.1 | Team Contract | --- | 1 | Bryce Coppadge | bar: 2020-02-03 to 2020-02-09
1.2 | Define Problem | 1.1 | 1 | Bryce Coppadge | bar: 2020-02-10
1.3 | Stakeholder Analysis | 1.2 | 2 | Bryce Coppadge | bar: 2020-02-10 to 2020-02-11
1.4 | Feasibility Analysis | 1.3 | 3 | Bryce Coppadge | bar: 2020-02-12 to 2020-02-16
1.5 | Risk Assessment | 1.3 | 2 | Bryce Coppadge | bar: 2020-02-13 to 2020-02-16
1.6 | Assess Team's Docker Knowledge | 1.4, 1.5 | 2 | Bryce Coppadge | bar: 2020-02-13 to 2020-02-19
2 | ANALYZE
2.1 | Assess PanDoc Capabilities |  | 3 | Joseph Wanat | bar: 2020-02-20 to 2020-02-28
2.2 | Develop Survey/Questions |  | 1 | Joseph Wanat | bar: 2020-02-25 to 2020-02-28
2.3 | Identify User Requirements | 2.2 | 4 | Joseph Wanat | bar: 2020-02-28 to 2020-03-06
2.4 | Determine Business Process Integration | 2.3 | 3 | Joseph Wanat | bar: 2020-03-04 to 2020-03-06
3 | DESIGN
3.1 | Determine Best Approach for Dockerfile | 1.6, 2.1 | 2 | Shraddha Venkatraman | bar: 2020-02-27 to 2020-03-05
3.2 | Determine Docker Dependencies | 3.1 | 2 | Shraddha Venkatraman | bar: 2020-03-05 to 2020-03-06
3.3 | Diagram Business Processes | 3.2 |  | Shraddha Venkatraman | bar: 2020-03-16 to 2020-03-17
4 | DEVELOP
4.1 | Create GitHub Reposititory | 1, 2, 3 | 1 | Robert Sonneliter | bar: 2020-03-18
4.2 | Code the System | 4.2 | 30 | Robert Sonneliter | bar: 2020-03-19 to 2020-04-05
5 | TEST
5.1 | Identify Bugs in Code | 4.2 | 8 | Nick Johnson | bar: 2020-03-23 to 2020-04-08
5.2 | Implement Bug Fixes | 3, 4, 5.2 | 4 | Nick Johnson | bar: 2020-04-06 to 2020-04-10
5.3 | Submit to Client for Revisions | 5.3 | 1 | Nick Johnson | bar: 2020-04-10
5.4 | Make Client Revisions | 5.4 | 3 | Nick Johnson | bar: 2020-04-11 to 2020-04-16
5.5 | Document Testing Results | 5.1 - 5.4 | 3 | Nick Johnson | bar: 2020-04-15 to 2020-04-19
6 | IMPLEMENT
6.1 | Create Handoff Plan for Stakeholders | 1, 2, 3, 4, 5 | 3 | Robert Sonneliter | bar: 2020-04-17 to 2020-04-19
6.2 | Present Solution | 6.1 | 1 | Robert Sonneliter | bar: 2020-04-20 to 2020-04-24